## Backlog
User | Story | Complextity | Priority | Status | Maturity | Notes
Earners | As an unauthorized user, I want to sign up, sign in and logout |  | 1 | Done | Intermediate (Further Development)
Earners | As an unauthorized user, I want to create and edit my profile |  | 1 | Done | Intermediate (Further Development)
Earners | As an earner, I want to browse projects (With Categories, tags, keywords). |  | 1 | To-Do
Earners | Create a script to purge to Database |  | 1 | To-Do |  | Search Projects; (Through Github or Excel Sheet or any tolls to show requirements)
Earners | As an earner, I want to apply for Projects (Individually or in a team) |  | 1 | To-Do
Earners | As an earner (Mentor), I can request higher payment (Cash/Token) for a certain Project |  | 1 | To-Do |  | if I applied with a shorter timeline, extra service and higher Quality. Optional if Client allows it!
Earners | As an earner, I want to sign the project contract |  | 2 | To-Do
Earners | As an earner, I want to access to an Advisory learning set. |  | 2 | Done | Low (Basic) | Through Google Drive
Earners | As an earner, I want to join forces in existing bids. |  | 2 | To-Do
Earners | As an earner, I want to see the list of projects I am working on with description, team, company and progress |  | 2 | To-Do
Earners | As an earner, I want to work and edit my project work (create a backlog, view and edit team members and Rank, Assign Roles, upload files, have a live workspace, Discussion space, Sharing learning materials, and comments.) |  | 3 | Done | Intermediate (Further Development) | Through Github and Google Drive (For Sharing Learning Materials in advisory learning set)
Earners | As an earner, I want to request mentorship and live discussion |  | 3 | To-Do
Earners | As an earner, I want to submit my deliverables. |  | 3 | Done | Low (Basic) | Through Github and Google Drive
Earners | As an earner, I want to see my tokens balance and decide on financial actions (exchange for cash, keep) |  | 3 | To-Do
Earners | As an earner, I want to review my rank (Apprentice, Senior, Mentor) |  | 3 | To-Do
Entreprises (Clients) | As an unauthorized user, I want to sign up, sign in and logout |  | 4 | To-Do
Entreprises (Clients) | As an unauthorized user, I want to create and edit my profile |  | 5 | To-Do
Entreprises (Clients) | As a client, I want to post projects (Name, Objective, Description, Category, Deadline, Budget) |  | 5 | To-Do
Entreprises (Clients) | As a client, I want to have the option of offering a rush delivery option with higher pay |  | 5 | To-Do
Entreprises (Clients) | As a client, I want to have the option of allowing earners to apply with different offers |  | 5 | To-Do
Entreprises (Clients) | As a client, I want to view applicants and bids. |  | 5 | To-Do
Entreprises (Clients) | As a client, I want to accept and reject bids. |  | 5 | To-Do
Entreprises (Clients) | As a client, I want to formulate and sign a project contract |  | 5 | To-Do
Entreprises (Clients) | As a client, I want to track project progress. |  | 6 | To-Do
Entreprises (Clients) | As a client, I want to contact project mentor and do a live call. |  | 6 | To-Do
Entreprises (Clients) | As a client, I want to give feedback and share comments on work progress. |  | 7 | To-Do
Entreprises (Clients) | As a client, I want to accept and reject submitted deliverables. |  | 7 | To-Do
Entreprises (Clients) | As a client, I want to proceed with payment. |  | 7 | To-Do
Experimentation | External Reviewer in case of disagreement (with 5% of the total payment) |  | 8 | To-Do
Experimentation | Only Mentor can be apply reviewer |  | 8 | To-Do
Experimentation | Reviewers can be other mentors |  | 8 | To-Do
Experimentation | Reviewing state is anonymous (Mentor, Client and earners); 3 Reviewers |  | 8 | To-Do
Experimentation | "Request Review" button |  | 8 | To-Do
Experimentation | Ranking for reviewer |  | 8 | To-Do
Experimentation | Accepting Reviewers (1 From Top 10 mentors, 1 Random, 1 from application) |  | 8 | To-Do
Experimentation | In case of not being satisfied from the results, I can chnage the reviewer (with 10% payment this time) |  | 8 | To-Do
Experimentation | As a client, I want to be able to rank earners |  | 8 | To-Do

## Definition of Done
"Done" Definiton
Earners Submit Final Version.
Clients accept submitted version with no more feedback